## page 1
Capability Objective | Issue / Area for Improvement | Corrective Action | Capability Element | Responsible Organization | Organization POC | Target Date | Completion Date
Healthcare Systems Preparedness | Many plan members have not accessed the LTC-MAP website and input the basic facility planning data including current contacts. | All LTC-MAP plan member facilities to enter at least three (3) current contacts (Administrators / Executive Directors, Directors of Nursing / Resident Care Directors and Maintenance Directors) in the Contacts Tab of their facility planning data tabs on the LTC-MAP website. (See Appendix D) | Planning | All LTC-MAP Members | Facility Administrators | 2021-12-31
Information Sharing | Many of the RAFs experienced difficulty in sending the Influx Logs via fax due to overall call volume and faxes not going through to the RCC in a timely fashion. | Further exploration of an e-mail address to use for the LTC-MAP and how the responder teams would have access to it needs to occur. Additional approaches may include pdf attachments on the incoming e-mails being deposited to a specific location where they may be retrieved from the web-based management system (e.g., on the ERS dashboard). | Planning | Jensen Hughes | Andy McGuire | 2021-12-31
Emergency Operations Coordination | Many Mutual Aid Plan member facilities have not implemented an incident command structure or are not using the Nursing Home Incident Command System (NHICS). | Plan members need to learn and implement the ICS system to be compliant with CMS Regulations. All plan members should review the NHICS website at: https://www.cahfdisasterprep.com/nhics to download and implement the tools of the NHICS and train their staff on use of the system. | Training | All LTC-MAP Members | Administrators | 2021-12-31
Emergency Operations Coordination | Some plan member facilities were challenged with setting up an effective Incident Command Center within their facilities. | Jensen Hughes developed a Facility Incident Command Center Guide (see Appendix G). All plan members should reference this guide to assure an effective location and setup of their facility incident command center. | Planning | All LTC-MAP Members | Administrators | December 31, 2021
Emergency Operations Coordination | Mutual Aid Plan members facilities were challenged with creating an Incident Action Plan (IAP) during the initial phases of the exercises. | Jensen Hughes has provided an Incident Action Plan (IAP) Guide (See Appendix I). All plan members should download this guide and incorporate it into their Incident Command Center tools and processes. | Planning | Jensen Hughes | Andy McGuire | 2021-12-31
Emergency Operations Coordination | Regional Coordinating Center Responders had difficulty matching up correct Categories of Care for more complex residents due to lack of Categories of Care information being current for all facilities. | Jensen Hughes distributed a Categories of Care Quick Guide (See Appendix E) for all plan members to use to update their Categories of Care. All Mutual Aid Plan member facilities need to assure their categories of care are correctly entered on the LTC-MAP website. | Planning | All LTC-MAP Members | Administrators | December 31, 2021
Emergency Operations Coordination | The Regional Coordinating Center needs maps for geographical spatial awareness of the facilities within the region. | Jensen Hughes to work with key partners to obtain maps plotted with all MAP member facilities and other key landmarks (major roadways, hospitals, etc.) for all NY MAP regions. | Planning | Jensen Hughes | Andy McGuire | 2021-12-31
Information Sharing | Some Mutual Aid Plan members struggled with the who, what, when, where and why, when requested to develop and submit a press release or statement. | Jensen Hughes developed a Press Release / Statement Template. All plan members should download this guide and incorporate it into their Incident Command Center tools and processes. (See Appendix J) | Training | All LTC-MAP Members | Administrators | 2021-12-31
Information Sharing | LTC-MAP Member Emergency Reporting | To facilitate increasing facility institutional knowledge on emergency reporting, Jensen Hughes has provided a Quick Reference Guide – How to Complete Emergency Reporting (see Appendix F). All Mutual Aid Plan member facilities need to practice emergency reporting and have at least three people from each facility that know how to complete emergency reporting when requested. | Training | All LTC-MAP Members | Administrators | 2021-12-31
Emergency Operations Coordination | Clinical assistance with resident transportation. | The LTC-MAP should consider adding a customized question to the transportation screen of emergency reporting to ascertain if the RAF has any available clinical staff (RN, LPN or CNA) to accompany the driver if they are providing transportation. | Planning | Jensen Hughes | Andy McGuire | 2021-11-30
Emergency Operations Coordination | Resident Accepting Facilities (RAFs) lacked the experience and tools to effectively operationalize a surge area. | Jensen Hughes to develop and distribute a Triage/Intake and Surge Capacity Guide for all NY MAP members. | Planning | Jensen Hughes | Andy McGuire | 2021-12-31